## Product Owner Rough Notes List
| Project Description | The Product Owner (PO) has been talking to the Business Owner for the project and come up with the list of desireable elements below. The project is a small portable Lego model of a bridge that the Business Owner wants created, in order to sell the concept to sponsors, the public, the media -- in order to generate interest on financing a real bridge.
Initial PO priority thoughts | Product Owner's Rough Notes list, not a Product Backlog, each row is NOT a PBI
| Item or note | Comment
1 | The roadway of the bridge is to be 4.8 cm wide and 30 cm long
2 | 4 pillars to support the roadway. pillars are 4.8 cm wide (to match the width of the road) by 5.2 cm high. The center of the bridge must have a minimum of a 12 cm opening
3 | Paper ramps, 4.8 cm wide by 20 cm long | 2 of these, they span from the end piers sloping down to the ground, they only touch the ground on one end and the end pier at the other.
4 | A paper roadway line running the length of the bridge to separate traffic | The paper roadway covers the entire structure of the roadway and has a solid line down the middle to separate traffic
5 | A "tent style" paper sign at both ends of the bridge, with the name of the bridge | 2 of these, 5cm high by 5 cm wide, with the name of "The Agile Bridge, 2015 Summer One"
6 | A model police car based on an 8 stud lego block with 4 other lego pieces but all of different sizes and all different colours | This model police car needs 2 small paper signs on the side with the words "Police"
7 | A model police van based on a 16 stud lego block with 7 other lego pieces using exactly 5 different sizes of blocks with exactly 3 colours
8 | Civilian car A - based on an 8 stud lego blocks, with 2 other lego pieces each a different size but in total exactly 1 colour
9 | Civilian car A - based on an 8 stud lego blocks, with 2 other lego pieces each a different size but in total exactly 2 colours
10 | Civilian car A - based on an 8 stud lego blocks, with 2 other lego pieces each a different size but in total exactly 3 colours
11 | An ambulance based on a 8 stud lego block, with 3 other lego pieces using exactly 3 different sizes of blocks and exactly 4 different colours | Just one, with 3 red cross paper signs on the ambulance
12 | Truck A - the base to be 2 studs wide and 4.8 cm long. 6 other lego pieces required, in total 2 colours | Each truck is to have 2 paper signs, one on each side, indicating the name of the trucking company, the names are to be real firms in London
13 | Truck B - the base to be 2 studs wide and 4.8 cm long. 6 other lego pieces required, in total 3 colours | Each truck is to have 2 paper signs, one on each side, indicating the name of the trucking company, the names are to be real firms in London
14 | Truck C - the base to be 2 studs wide and 4.8 cm long. 6 other lego pieces required, in total 4 colours | Each truck is to have 2 paper signs, one on each side, indicating the name of the trucking company, the names are to be real firms in London
15 | Truck D - the base to be 2 studs wide and 4.8 cm long. 6 other lego pieces required, in total 5 colours | Each truck is to have 2 paper signs, one on each side, indicating the name of the trucking company, the names are to be real firms in London
16 | A boat based on using mutiple lego pieces as the base, with the dimensions of 10 studs by 4 studs. Total of exactly 10 pieces of lego, 6 different colours, 6 different types of pieces.
17 | A paper roadway to emulate asphalt, that is 30 cm long by 10 cm wide, that starts where the ramp ends and runs away from the bridge | 2 of these, one before each ramp, with a dashed center line.
18 | Paper trees 10 cm high, coniferous trees, coloured green | 6 of these, they have to stable and standup by themselves
19 | Paper trees 12, cm high, deciduous trees, coloured green with brown trunks | 4 of these
20 | A paper "river" on each side of the middle pier. Each paper to be 20 cm by 25 cm (this latter dimension perpindicular to the bridge), | Each "river" paper to have a blue meandering river drawn on it that is 10 cm wide in blue, with the river banks being green and brown.
21 | Each sub-assembly of the model bridge is to be portable, which means it should be made such that can easily be separated from the rest of the bridge without having to dis-assemble other components. | For portability, the sizes of the lego sub-assemblies should be no larger than what can fit into a common grocery store fabric shopping bag, 36 cm by 36 cm when flat.
22 | Paper tree stability, each has to have it's own paper base stand so they don't fall over | Stands are to be coloured green.
23 | Measurements provided in cm are + or - 1mm

## Product Backlog
| What is your definition of done? | The bridge is usable commuters and is high enough to allow shipping vessesl to pass below.
| Product Backlog |  | Enter your acceptance criteria, in your Sprint Review (demo) what would the PO be looking for before you can demo?
Priority | Story or Feature | DA | Acceptance Criteria | Estimate in T-Shirt sizes
1 | Set the Pillars: As a ship captain, I need the columns to be higher than 5.1cm tall so that my vessel to pass. As a seafarer, I need the inner columns to be 12cm apart so that the multiple boats can safely pass without hitting the columns. | Day 1 | There are 4 columns, 5.2cm high x 4.8cm wide wit a 12 cm space from the centre of the bridge | X-Large
2 | Build the Bridge As the mayor of Change Master’s village, I need the bridge to be 30cm wide to connect the two villages and 4.8cm wide allowing two way traffic to flow seamlessly. | Day 1 | The bridge is 30cm long by 4.8cm wide | X-Large
3 | Create Ramps As a truck driver, I would like the ramps on the bridge to be 20cm long so that my vehicle can get on and off the bridge without being damaged | Day 1 | There are 2 ramps at each end of the bridge that are 4.8cm wide by 20cm long | Large
4 | Bridge Signage As the mayor of Change Master’s village, I need the bridge to have signs at the front and back of the bridge with the village’s name so visitors will know when they are entering and leaving | Day 2 | There are two signs on the bridge: 5cm high by 5cm wide | Medium
5 | Making the Roadway As the mayor, the bridge must connect with the new major roads leading to and from the city. | Day 2 | 30cm long by 10cm wide (this needs verification) | Medium
6 | Have Vehicles (emergency) As an engineer of the bridge, I need the village’s police and ambulance vehicles to test the usability of the bridge and ensure they can pass in event of an emergency. | Day 2 | 1 police car, 1 police van, 1 ambulance | Small
9 | Have Vehicles (regular) As an engineer of the bridge, I need various cars and trucks to test the max weight capacity and the tallest boat in the village to pass below to confirm the height of the bridge. | Day 2 and 3 | 3 civilian cars, 4 trucks and 1 boat | Small
10 | Preserve Trees As a city official, the existing 6 coniferous trees and 4 deciduous trees must not be damaged by the bridge construction as they are part of our village’s nature preservation law. | Day 3 | 6 coniferous 10cm high, 4 deciduous 12cm high | Small
11 | River Runs Deep As a the village's waterway's expert, the bridge must not affect the current flow of the river as it will confict with our village's nature preservation law | Day 3 | 30cm long by 20cm wide, below the columns | X-Small
12 | Making the Roadlines As a driver, I would like lines on the bridge to separate the two lanes so I don’t accidentally go onto the opposite side. | Day 2 | There is a line evenly separating the two lanes of traffic | X-Small

## Sprint 1 Backlog
| Sprint 1 Goal |  | Enter the goal of your Sprint 1
| Team Capacity, assume you have four 10 minute "days" in your Sprint |  | Enter your calculations in text format, for what your team capacity is in "Real Minutes", and how you estimated it | Enter your team capacity in real minutes, a number
Select the highest priority Features or Stories for your Sprint | Sprint 1 Backlog |  | For the purposes of this exercise, use between 2 and 4 tasks for each story. | Estimate each task in ideal minutes
| Story or Feature |  | Tasks | Estimate in Real Minutes | Comments
| 1. Set the Pillars | 1.1 | Gather the Materials | 2
|  | 1.2 | Confirm Dimensions of Legos (QC) | 1
|  | 1.3 | Build Pillars | 4
|  | 1.4 | Confirm Build (QC) | 1
|  |  | Total | 8
| 2. Build the Bridge | 2.1 | Gather the Materials | 2
|  | 2.2 | Confirm Dimensions of Legos (QC) | 1
|  | 2.3 | Build Bridge | 6
|  | 2.4 | Add Road Lines | 1
|  |  | Total | 10
| 3. Create Ramps | 3.1 | Gather the Materials | 1
|  | 3.2 | Set the Dimensions | 5
|  | 3.3 | Fold and Tape the Ramp | 3
|  | 3.4 | Confirm Build (QC) | 1
|  |  | Total | 10
| 4. Bridge Signage | 4.1 | Gather the Materials | 1
|  | 4.2 | Confirm Vehicle Scale | 2
|  | 4.3 | Confrim Dimensions for Signage | 1
|  | 4.4 | Create Signage | 5
|  |  | Total | 9
| 5. Make the Roadway | 5.1 | Confirm Dimensions of Roadway | 1
|  | 5.2 | Create Roads of 30 cm long and 10 cm wide which connects ramp end. | 3
|  |  | Total | 4
| 6. Have Vehicles (emergency) | 6.1 | Gather the Materials | 2
|  | 6.2 | Build Vehicles of 4.8 cm long and having 2, 3 ,4 ,5 colours in the set of different colours. | 5
|  |  | Confirm dimensions and set of colours accordingly | 1
|  |  | Total | 8
| 7. Have Vehicles (regular) | 7.1 | Gather the Materials | 3
|  | 7.2 | Build First Set of Vehicles | 6
|  | 7.3 | Build Second Set of Vehicles | 6
|  | 7.4 | Confirm Dimensions | 5
|  |  | Total | 20
| 8. Preserve Trees | 8.1 | Gather the Materials | 1
|  | 8.2 | Set the Designs | 4
|  | 8.3 | Cut Trees of 10 cm and 12 cm | 3
|  | 8.4 | Build Trees of the dimensions | 2
|  |  | Total | 10
| 9. River Runs Deep | 9.1 | Get the Materials | 1
|  | 9.2 | Check the Measuresuments | 1
|  | 9.3 | Cut/Tape the Sheets together | 3
|  | 9.4 | Install the River | 1
|  |  | Total | 6
| 10. Make the Roadlines | 10.1 | Get the Measurements | 1
|  | 10.2 | Cut the Strips | 2
|  | 10.3 | Install Strips onto Bridge | 2
|  | 10.4 | Task 4
|  |  | Total | 5

## Sheet1 (hidden)
| Sprint 1 Goal | Enter the goal of your Sprint 1
| Team Capacity, assume you have four 10 minute "days" in your Sprint | Enter your calculations in text format, for what your team capacity is in "Real Minutes", and how you estimated it | Enter your team capacity in real minutes, a number
Select the highest priority Features or Stories for your Sprint | Sprint 1 Backlog | For the purposes of this exercise, use between 2 and 4 tasks for each story. | Estimate each task in ideal minutes
| Story or Feature | Tasks | Estimate in Real Minutes | Comments
| Example, a | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0
| Enter another feature | Task 1 | 0
Task 2
Task 3
Task 4
|  | Total | 0